## Test Plan
Section | Item | Details
Test Plan Information | Project Name | ShopnoJob Web Application
Test Plan Information | Website | https://sopnojob.com/
Test Plan Information | Testing Type | Manual Functional, UI, Usability, Compatibility and Basic Performance Testing
Test Plan Information | Platforms | Desktop Web and Mobile Web
Test Plan Information | Testing Approach | Black-box manual testing
Objective | Purpose | Verify that ShopnoJob functions correctly and consistently on desktop and mobile web browsers.
Objective | Coverage | Functional correctness, validation, navigation, responsive UI, compatibility, usability and basic performance.
Desktop Scope | Home Page | Page loading, navigation, content, buttons and links
Desktop Scope | Registration | Valid/invalid registration, required fields, password validation and verification
Desktop Scope | Email Verification | Verification link and resend functionality
Desktop Scope | Login | Valid/invalid credentials, password visibility and session behavior
Desktop Scope | Forgot Password | OTP request, validation, resend and password reset
Desktop Scope | Profile | View/edit/save personal information
Desktop Scope | Education | SSC, HSC and graduation information
Desktop Scope | MCQ Practice | Questions, options, navigation, submission and results
Desktop Scope | Model Test | Test setup, start, submission and results
Desktop Scope | Resume Test | Continue from previous progress or restart
Desktop Scope | Wrong Answers | Review incorrect questions and retake
Desktop Scope | Progress | Question count, accuracy, streak and readiness information
Desktop Scope | Search | Valid, invalid, partial and empty searches
Desktop Scope | Exam Information | Exam name, date, time and save functionality
Desktop Scope | Premium | Premium-content access/restriction behavior
Desktop Scope | Logout/Delete Account | Logout and account deletion flow
Mobile Scope | Responsive Layout | Content fits different mobile screen sizes without overlap or unwanted horizontal scrolling
Mobile Scope | Touch Interaction | Buttons, links, menus, inputs and scrolling
Mobile Scope | Authentication | Registration, login, verification, OTP and password reset
Mobile Scope | Profile | Profile and education editing on small screens
Mobile Scope | MCQ/Model Test | Question visibility, answer selection, navigation, submission and resume
Mobile Scope | Search | Search input, results and mobile keyboard behavior
Mobile Scope | Orientation | Portrait and landscape layout
Mobile Scope | Browser Compatibility | Chrome Android, Safari iOS and other supported mobile browsers
Mobile Scope | Performance | Basic loading and responsiveness checks
Functional Testing | Authentication | Register, verify email, login, forgot password, OTP, reset password and logout
Functional Testing | Profile | Edit personal information and educational qualifications; verify persistence
Functional Testing | MCQ/Model Test | Start, answer, navigate, submit, score, review and resume
Functional Testing | Progress | Verify streak, completed questions, accuracy and readiness information
Functional Testing | Search | Search by subject, chapter or question; validate empty/invalid input
UI/UX Testing | Desktop | Alignment, spacing, fonts, buttons, icons, forms, navigation and error messages
UI/UX Testing | Mobile | Responsive layout, touch targets, text wrapping, keyboard behavior, menus and pop-ups
Compatibility | Desktop Browsers | Chrome, Edge, Firefox and Safari where available
Compatibility | Mobile Browsers | Chrome Android, Safari iOS, Samsung Internet and Firefox Mobile where applicable
Responsive Testing | Desktop | 1920x1080, 1366x768, 1280x720
Responsive Testing | Tablet | 768x1024, 1024x768
Responsive Testing | Mobile | 360x800, 375x812, 390x844, 412x915
Validation | Input Validation | Check empty, invalid, incorrect-format and boundary inputs across forms
Performance | Basic Manual Checks | Observe loading and response times for home, login, search, tests, results and profile save
Security | Basic Functional Checks | Password masking, protected pages, logout/session behavior, OTP validation and data exposure
Entry Criteria | Requirements | Website accessible, test environment available, test accounts/data available and major functionality deployed
Exit Criteria | Completion | Planned cases executed, major defects reported, retesting/regression completed and test summary prepared
Defect Severity | Critical | Application/function unusable or major data/security issue
Defect Severity | High | Important functionality does not work
Defect Severity | Medium | Function works incorrectly but workaround exists
Defect Severity | Low | Minor UI, wording or cosmetic issue
Deliverables | Documents | Test Plan, Desktop Test Cases, Mobile Test Cases, Test Execution, Bug Reports and Test Summary

## Desktop vs Mobile
Test Area | Desktop Version | Mobile Version
Functional Testing | Full functional workflow | Same functional workflow
Navigation | Header/sidebar/navigation links | Mobile menu/navigation and back behavior
Forms | Keyboard/mouse input | Touch input and mobile keyboard
MCQ | Question and option layout | Question/option fit and touch selection
Model Test | Start, resume, submit and results | Same plus small-screen usability
Responsive UI | Desktop layouts | Portrait/landscape and multiple widths
Browsers | Chrome, Edge, Firefox, Safari | Chrome Android, Safari iOS, Samsung Internet
Performance | Page and feature response | Loading/response under mobile conditions
UI | Alignment, spacing, fonts, controls | No overlap, readable text, usable touch targets
Compatibility | Different desktop browsers/resolutions | Different devices, browsers and orientations