## Bug Report
ShopnoJob Desktop Version — Bug Report
Summary | Value
Total Bugs | 2
Open/New Bugs | 2
Bug ID | Requirement ID | Test Case ID | Module | Bug Summary | Preconditions | Steps to Reproduce | Test Data | Expected Result | Actual Result | Severity | Priority | Environment | Status | Reported By | Reported Date | Impact / Notes
BUG_001 | REQ_006 | TC_015 | Model Test | Incomplete model test does not resume from the last unanswered question and previous answers are not retained | User is logged in and has previously started but not completed a model test. | 1. Log in to the application. 2. Open Model Test. 3. Start a test and answer some questions. 4. Exit before completing the test. 5. Re-enter the same chapter/test. 6. Choose the option to continue with the next questions. 7. Observe the resumed question and previous answers. | Existing incomplete test progress | The test should resume from the last unanswered question and all previously selected answers should remain retained. | The test does not resume from the last unanswered question, and previous answers are not retained. | Medium | Medium | Desktop | New | Israt | 25-08-2026 | Users can lose test progress and must repeat previously answered questions, reducing usability and trust in the Model Test feature.
BUG_002 | REQ_009 | TC_020 | Profile | Profile name cannot be saved because Education Qualification validation blocks the update | User is logged in and is on the Profile/Edit Profile page. | 1. Log in to the application. 2. Open Profile. 3. Edit the full name to a valid new value. 4. Leave Education Qualification empty. 5. Click Save. 6. Observe the validation message and whether the name is updated. | New name: Test User QA | The name should update successfully and be reflected on the profile page immediately. | The profile cannot be saved. The system displays: 'Education qualification field may not be empty.' | Medium | Medium | Desktop | New | Israt | 25-08-2026 | A user cannot update the name independently when Education Qualification is empty, creating an unnecessary dependency between profile fields.
Source: Failed test cases extracted from “sopnojob_test_cases desktop version.xlsx” (TC_015 and TC_020).